Travel Case

Product Requirements Document (PRD)

Sabre internship deliverable  |  Draft v1  |  July 27, 2026  |  Companion to: Travel Case SRS

# 1. Purpose of This Document

This PRD sits upstream of the Travel Case Software Requirements Specification (SRS). The SRS defines detailed, API-level functional and technical requirements for the development team. This PRD defines the product rationale: the problem, the users, what is actually a priority given the timeline, and what still needs a decision before build. Where content overlaps with the SRS (functional requirements by vertical), this document summarizes; the SRS remains the source of technical detail.

# 2. Product Overview

Travel Case is a full-service Online Travel Agency (OTA) built on Sabre's GDS — flights, hotels, and car rentals under a single integration — extended with airport transfers, travel insurance, and activities/tours, serving both individual travelers (B2C) and reselling travel agents (B2B) from launch. Benchmarked against Priceline, Opodo, Kiwi.com, and Ixigo.

Working assumption (not yet confirmed with a product sponsor): Sabre requires a direct-facing OTA product covering its own GDS content plus adjacent services, for both retail travelers and reselling agents. This should be confirmed rather than treated as settled — see Section 16.

# 3. Goals & Success Metrics

TBD — intentionally left open. No acquisition, GMV, booking-volume, or conversion targets have been defined or assumed. These need to come from product/business stakeholders before build kickoff, since they should drive prioritization decisions in Section 5, not follow from them.

# 4. Target Users

## 4.1 B2C — Individual Traveler

Searches and books flights, hotels, cars, and add-on services for their own trip, ideally in one flow. Needs: transparent pricing across all verticals, one unified checkout/cart where possible, a single confirmation for a multi-part trip.

## 4.2 B2B — Reselling Travel Agent

Books across all verticals on behalf of clients at agent rates. Needs: fast approval, visible markup/commission per vertical, consolidated booking history across flights/hotels/cars/services.

# 5. Scope & Prioritization

Requested scope: five verticals (flights, hotels, cars, transfers + insurance, activities/tours), B2C + B2B, web only, inside a 1–3 month build window.

| Tier | Scope | Rationale |
| --- | --- | --- |
| P0 — Day one | Flights, hotels, car rentals via Sabre; core B2C booking + unified checkout; core B2B layer (registration, approval, per-vertical markup, dashboard) | Sabre certification is the fixed critical-path constraint regardless of any other decision — this is the one thing that must start week 1 |
| P1 — Fast-follow, target within MVP window | Airport transfers, travel insurance | Separate, smaller integrations outside Sabre's scope; can run in parallel without blocking certification |
| P2 — Recommended fast-follow after MVP launch | Activities/tours (Viator/GetYourGuide-style) | Requested as in-scope for MVP, but see the risk flag below before treating this as fixed |

Risk flag: activities/tours in the MVP The SRS already treats 4 verticals in 1–3 months as tight, with single-vendor Sabre certification as the one mitigating factor. Adding activities/tours is a third non-Sabre integration (alongside transfers and insurance), on a timeline where the fixed 4–8 week certification window already consumes most of the available time. My recommendation is to sequence activities/tours as a post-launch fast-follow. If it stays in the MVP as requested, the 1–3 month window should be treated as no longer realistic — either the timeline extends or something else moves out. This is a decision for whoever owns the timeline commitment, not something to quietly absorb.

# 6. Functional Capabilities by Vertical (Summary)

Full API-level requirements are specified in the SRS, Section 6. Summary:

- Flights: search/filter by price, duration, stops, airline; fare rules shown pre-purchase; e-ticket/PNR via email.

- Hotels: search/filter by price, star rating, guest rating, amenities; cancellation policy shown pre-booking. Known constraint: Sabre's hotel photography/branding is weaker than dedicated hotel platforms — plan UI fallback treatment (consistent card sizing, fallback imagery).

- Car rentals: search/filter by price, vehicle type, transmission, supplier; insurance/excess terms shown pre-booking.

- Transfers + insurance: add-ons offered at checkout, sourced via separate provider/affiliate integrations outside Sabre.

- Activities/tours: not yet specified at API/vendor level — needs its own scoping pass if it stays in MVP (see Section 5).

# 7. Cross-Vertical Requirements (Summary)

- Unified cart/checkout: pay once for a multi-vertical trip, not per component.

- Single trip confirmation summarizing all booked components, each with its own supplier reference attached.

- One login, one booking history view across all verticals.

# 8. B2B Agent Layer (Summary)

- Agent sign-up with business verification; admin approval before activation.

- Agent-specific pricing/markup applied consistently across verticals (see Section 10 for recommended bands).

- Agent booking history and commission reporting across all verticals in one dashboard.

- Deferred (out of MVP): white-label branding, sub-agent hierarchies, credit/wallet booking, bulk booking tools.

# 9. Payments & Currency Strategy

Recommendation: launch with four currencies — NGN (home market), USD (dominant travel-booking currency and largest diaspora corridor), GBP, and EUR (the two other major diaspora/travel corridors into Nigeria and West Africa). “Global” as stated is not a realistic MVP currency list; a genuinely global set (100+ currencies) is not something an MVP should try to support. This is a recommendation, not a confirmed decision — it needs sign-off from whoever owns pricing/markets.

Payment gateways: at least one gateway for Nigeria/Africa (e.g., Paystack or Flutterwave) plus one for international cards (e.g., Stripe). PCI-DSS compliance required — no raw card data stored, tokenization via gateway.

# 10. Commission / Markup Model

What this covers: whether a B2B agent earns the same percentage markup regardless of what they book, or whether the percentage differs by vertical. Industry norm is that it differs — airline commissions are thin because GDS/airline rules already cap them, while hotels, cars, and affiliate-style add-ons carry fatter margins. Recommended starting bands, pending confirmation from Sabre's commercial team:

| Vertical | Recommended Band | Why |
| --- | --- | --- |
| Flights | ~3–5% | GDS/airline commission structures leave little room |
| Hotels | ~10–12% | Standard OTA hotel margin range |
| Car rentals | ~8–10% | Mid-range margin, between flights and hotels |
| Transfers / insurance | ~15–20% | Affiliate-style products typically pay the highest rate |

These are starting-point figures based on general OTA industry practice, not numbers specific to Travel Case's actual supplier agreements. Treat as a draft for the commercial team to confirm or correct.

# 11. Non-Functional Requirements (Pointer)

Full detail in SRS Section 11: HTTPS everywhere, tokenized payments, encrypted PII, role-based access control; search latency across three supplier APIs must be parallelized, not chained; IATA/airline ticketing rules; NDPR/GDPR depending on user base.

# 12. Assumptions & Dependencies

- Internal Sabre initiative — no external GDS contract or procurement dependency; sandbox/dev credentials are an internal request, not a vendor negotiation. This removes a risk the SRS had flagged as open.

- Sabre certification (4–8 weeks) remains the fixed critical-path constraint no matter what else is decided — it should start in week 1, in parallel with non-Sabre-dependent work.

- “Travel Case” is confirmed as a distinct project from the earlier “Travelbox” project, with no shared codebase or assets expected.

- Development team and budget are already in place (per SRS Section 13) — this document assumes no hiring/procurement delay.

- The currency list (Section 9) and commission bands (Section 10) above are recommendations pending sign-off, not confirmed product decisions.

# 13. Risks

| Risk | Likelihood | Impact | Recommendation |
| --- | --- | --- | --- |
| 5-vertical scope (incl. activities/tours) in 1–3 months | High | High | Defer activities/tours to post-launch, or extend the timeline — don't absorb silently |
| Sabre certification consumes most of the build window | High | High | Start certification submission in week 1, no exceptions |
| Hotel content quality weaker than dedicated hotel platforms | Medium | Medium | Design UI fallback treatment (card sizing, fallback imagery) up front |
| Multi-supplier search latency (flights + hotels + cars) | Medium | Medium | Parallelize supplier API calls; never chain them |
| Currency & commission decisions still pending sign-off | Medium | High | Resolve before payments/commission engineering starts, not mid-build |

# 14. Timeline & Milestones

| Timeframe | Activity |
| --- | --- |
| Week 1 | Sabre sandbox integration + certification submission begins; transfers/insurance integration scoping starts in parallel; UI/UX and non-GDS build (accounts, admin, agent approval workflow) begins concurrently |
| Weeks 1–8 | Sabre certification runs in parallel with build — this is the critical path for the whole MVP |
| Weeks 2–6 | B2C + B2B core build across flights, hotels, and car rentals |
| Weeks 4–8 (if in scope) | Transfers + travel insurance integration and checkout add-on flow |
| Post-certification | Production go-live gated by Sabre's certification sign-off, not internal readiness alone |
| Post-MVP (recommended) | Activities/tours integration and launch, once core verticals are stable |

# 15. Out of Scope (MVP)

- Native mobile app (web only, responsive)

- White-label B2B branding / full white-label portal

- Sub-agent hierarchies

- Credit/wallet-based booking for agents

- Bulk booking tools

- Cross-airline “virtual interlining” (Kiwi.com-style)

# 16. Open Items Requiring Sign-off

- Confirm final currency list and payment gateway priority (recommendation: NGN/USD/GBP/EUR, Paystack or Flutterwave + Stripe)

- Confirm commission/markup bands per vertical (recommendation given in Section 10)

- Confirm whether activities/tours stays P0 or moves to P1/post-launch given the timeline impact

- Define goals & success metrics (Section 3) with product/business stakeholders

- Confirm the internal Sabre stakeholder(s) who sign off at each milestone